## MVP Sprint
CODEPET — 1-Week MVP Sprint
Goal: Ship Full Game Loop (Lite) to TestFlight + App Store · Apr 7–13, 2026
MVP Scope: Auth + Onboarding + Lessons + Pet Care + Hearts + Coins · Cut: Compendium, Cosmetics, Pet Abilities, Idle XP, Dark Mode
# | Day | Role | Task | Priority | Est. | Status | Notes
1 | Mon Apr 7 | BE | Confirm unified CodePet-Clean project builds in Xcode (0 errors) | P0 | 1h | Not Started | GameState.swift emptied, assets copied
2 | Mon Apr 7 | BE | Register GameState as @EnvironmentObject in CodePetApp.swift | P0 | 30m | Not Started | Add .environmentObject(gameState)
3 | Mon Apr 7 | BE | Wire GamePersistence save/load into app lifecycle (onAppear/onDisappear) | P0 | 1h | Not Started | cp_game_ prefixed UserDefaults keys
4 | Mon Apr 7 | FE | Integrate PetCareView into HomeView (replace/augment PetAreaView5) | P0 | 2h | Not Started | Mood, energy bars, feeding
5 | Mon Apr 7 | FE | Add WelcomeBackView overlay to MainTabView on app return | P1 | 1h | Not Started | processReturnFromIdle on appear
6 | Tue Apr 8 | BE | Implement hearts regen timer (1 heart per 30 min) | P0 | 2h | Not Started | Background timer + foreground check
7 | Tue Apr 8 | BE | Wire coin earn logic into lesson completion handler | P0 | 1h | Not Started | 10 coins/lesson, 5 coins/streak day
8 | Tue Apr 8 | FE | Add HeartsDisplayView to LessonModalView header | P0 | 1h | Not Started | Show 5 hearts, lose on wrong answer
9 | Tue Apr 8 | FE | Wire loseHeart() on wrong answers + block lesson at 0 hearts | P0 | 1h | Not Started | Show refill sheet when blocked
10 | Tue Apr 8 | FE | Heart refill sheet (spend 20 coins to restore all hearts) | P1 | 1h | Not Started
11 | Tue Apr 8 | FE | Coin balance display in GameHUDBar (already exists — verify working) | P1 | 30m | Not Started | Top bar shows coins + streak
12 | Wed Apr 9 | BE | Test Google Sign-In end-to-end (button → auth → main app) | P0 | 2h | Not Started | Already implemented — needs e2e test
13 | Wed Apr 9 | BE | Test email/password auth flow (sign up + sign in + reset) | P0 | 1h | Not Started
14 | Wed Apr 9 | BE | Cloud sync: save essential state to Firestore on every progress change | P0 | 2h | Not Started | coins, hearts, completedLessons, pet stats
15 | Wed Apr 9 | BE | Cloud sync: load from Firestore on sign-in (restore progress) | P0 | 1h | Not Started | CloudSyncService already implemented
16 | Wed Apr 9 | FE | Fix any auth UI bugs found during testing | P0 | 1h | Not Started
17 | Thu Apr 10 | QA | Full new-user walkthrough: splash → onboard → character → first lesson | P0 | 2h | Not Started | Test all paths
18 | Thu Apr 10 | QA | Test returning user flows: sign-in → restore progress → continue | P0 | 1h | Not Started
19 | Thu Apr 10 | QA | Hearts edge cases: 0 hearts blocks, regen across restart, refill works | P0 | 1h | Not Started
20 | Thu Apr 10 | QA | Pet care: feeding costs coins, mood updates, energy decay after idle | P0 | 1h | Not Started
21 | Thu Apr 10 | FE | Fix all bugs found during QA | P0 | 2h | Not Started
22 | Thu Apr 10 | FE | UI polish: animations, transitions, visual consistency | P1 | 1h | Not Started
23 | Fri Apr 11 | BE | Set version 1.0.0 (build 1) in Xcode project settings | P0 | 15m | Not Started
24 | Fri Apr 11 | BE | Archive build and upload to App Store Connect | P0 | 1h | Not Started | Product → Archive → Distribute
25 | Fri Apr 11 | BE | Enable TestFlight and add beta testers | P0 | 30m | Not Started
26 | Fri Apr 11 | QA | Test TestFlight install on a second Mac | P0 | 1h | Not Started
27 | Fri Apr 11 | Mktg | Draft App Store description and keywords | P1 | 1h | Not Started
28 | Fri Apr 11 | Mktg | Prepare 3-5 App Store screenshots | P1 | 2h | Not Started
29 | Sat Apr 12 | BE | Review and fix any TestFlight crash reports | P0 | 1h | Not Started
30 | Sat Apr 12 | Mktg | Finalize App Store listing (description, screenshots, privacy policy) | P0 | 2h | Not Started
31 | Sat Apr 12 | Mktg | Publish privacy policy and support URL | P0 | 1h | Not Started | Required for App Store
32 | Sat Apr 12 | BE | Submit app for App Store Review | P0 | 30m | Not Started
33 | Sun Apr 13 | QA | Address any App Store review feedback | P0 | 2h | Not Started | If rejected, fix and resubmit
34 | Sun Apr 13 | FE | Final polish based on TestFlight tester feedback | P1 | 2h | Not Started

## Daily Focus
Daily Focus & Goals
Day | Theme | End-of-Day Goal
Mon Apr 7 | Build & Integration | App compiles clean, pet care visible on Home, GameState wired
Tue Apr 8 | Hearts & Economy | Hearts work in lessons, coins earned on completion, HUD shows both
Wed Apr 9 | Auth & Cloud Sync | All 3 auth methods tested, progress saves to Firestore and restores
Thu Apr 10 | QA & Polish | Full walkthrough passes, all bugs fixed, animations smooth
Fri Apr 11 | TestFlight Upload | Build uploaded, beta testers can install and play
Sat Apr 12 | App Store Submit | Listing complete, app submitted for review
Sun Apr 13 | Buffer Day | Address feedback, fix any review rejections

## Cut from MVP
Features Cut from MVP (ship in v1.1)
Feature | Why Cut | Target Version
Compendium | Nice-to-have collection feature, not core learning loop | v1.1
Cosmetic Shop | Monetization layer, not needed for beta validation | v1.1
Pet Abilities | Adds depth but not required for MVP engagement | v1.1
Idle XP (polish) | Basic return overlay works, detailed XP calc can wait | v1.1
Dark Mode | Visual preference, not functional blocker | v1.1
Sound Effects | Enhancement, not critical for first impression | v1.1
Mystic Grove 320×200 | Currently 240×150, visual upgrade can wait | v1.1
Economy Balancing | Ship with defaults, tune based on beta feedback | v1.1

## Ship Checklist
TestFlight & App Store Ship Checklist
# | Item | Done?
1 | Clean build (0 errors, 0 warnings except Google SDK)
2 | GameState @EnvironmentObject registered in CodePetApp.swift
3 | Pet care (mood, feeding, energy) working on Home tab
4 | Hearts system working in lessons (lose, regen, refill)
5 | Coins earned on lesson completion, displayed in HUD
6 | Google Sign-In working end-to-end
7 | Email/password auth working (sign up, sign in, reset)
8 | Anonymous auth working (skip sign-in path)
9 | Cloud sync: saves progress to Firestore
10 | Cloud sync: restores progress on sign-in
11 | Full new-user onboarding flow tested
12 | Returning user sign-in flow tested
13 | Version set to 1.0.0 (build 1)
14 | App icon and launch screen correct
15 | Provisioning profiles and code signing configured
16 | Archive uploaded to App Store Connect
17 | TestFlight enabled, beta testers invited
18 | App Store description written
19 | App Store screenshots uploaded (3-5)
20 | Privacy policy URL published
21 | Support URL published
22 | App submitted for App Store Review