## Overview
CODEPET — 3-Month Sprint Plan
Goal: Polished TestFlight Beta · 6 Game Systems · Apr 14 – Jul 5, 2026
Sprint | Dates | Theme | Key Deliverables | FE Tasks | BE Tasks | QA Tasks
Sprint 1 | Apr 14–27 | Foundation & Integration | Game systems backend merged, GameState wired, basic pet care visible | Wire PetCareView into Home, WelcomeBackView overlay | Merge GameSystems.swift, AppState+GameSystems, GamePersistence into project | Verify build compiles, test pet mood states
Sprint 2 | Apr 28–May 11 | Hearts & Economy Core | Hearts system live in lessons, coin economy working, basic shop | HeartsView in lessons, coin display in top bar, CosmeticShopView | Hearts regen timer, coin earn/spend logic, economy balancing | Hearts edge cases, coin balance integrity, economy exploit testing
Sprint 3 | May 12–25 | Compendium & Idle XP | Compendium browsable, idle XP on return, pet abilities UI | CompendiumView in Skills tab, idle XP return overlay polish | Compendium unlock triggers, idle XP calculation, pet abilities data | Compendium unlock accuracy, idle XP timing, cross-system regression
Sprint 4 | May 26–Jun 8 | Polish & Cloud Sync | Cloud sync for all game state, Google Sign-In working, UI polish pass | Polish all 6 system UIs, animation refinements, dark mode support | Firestore schema for GameState, cloud sync on every change, Google Sign-In e2e | Cloud sync conflict testing, auth flow testing, full onboarding QA
Sprint 5 | Jun 9–22 | Content & Balance | All 16 lessons reviewed, economy balanced, cosmetics complete, sound effects | Lesson content polish, cosmetic preview animations, sound integration | Lesson content review, economy balance tuning, 18 compendium entries finalized | Full playthrough testing (new user → all tiers), balance feedback
Sprint 6 | Jun 23–Jul 5 | TestFlight Prep & Launch | TestFlight build uploaded, App Store metadata ready, beta testers invited | Final bug fixes, performance optimization, screenshot generation | Build versioning, provisioning profiles, crash reporting setup | Full regression suite, device testing, beta tester onboarding
Agent Roles:
FE | Frontend — SwiftUI views, animations, UI polish
BE | Backend — Models, logic, persistence, Firebase, cloud sync
QA | Quality Assurance — Testing, regression, device coverage
Marketing | App Store listing, screenshots, beta outreach, social

## Task Backlog
ID | Sprint | Role | Task | Priority | Est. (hrs) | Status | Notes
1 | 1 | BE | Copy GameSystems.swift, AppState+GameSystems.swift, GamePersistence.swift into project | P0 | 2 | Not Started | Follow game-systems/README
2 | 1 | BE | Register GameState as @EnvironmentObject in CodePetApp.swift | P0 | 1 | Not Started
3 | 1 | BE | Wire GamePersistence save/load into app lifecycle | P0 | 2 | Not Started | cp_game_ prefixed keys
4 | 1 | FE | Integrate PetCareView into HomeView (replace/augment PetAreaView5) | P0 | 3 | Not Started
5 | 1 | FE | Add WelcomeBackView overlay to MainTabView | P1 | 2 | Not Started | processReturnFromIdle on appear
6 | 1 | FE | Pet mood emoji + status display on Home dashboard | P1 | 2 | Not Started
7 | 1 | QA | Verify project compiles with all new files on feature/game-systems | P0 | 1 | Not Started
8 | 1 | QA | Test pet mood transitions (all 8 states) | P1 | 2 | Not Started
9 | 1 | QA | Test energy/hunger decay after background time | P1 | 2 | Not Started
10 | 2 | BE | Implement hearts regen timer (1 heart / 30 min) | P0 | 3 | Not Started
11 | 2 | BE | Coin earn logic: lessons(10), challenges(25), streaks(5), level-ups(20) | P0 | 3 | Not Started
12 | 2 | BE | Coin spend logic: food, streak freeze, heart refill, cosmetics | P0 | 2 | Not Started
13 | 2 | FE | Add HeartsDisplayView to LessonModalView header | P0 | 2 | Not Started
14 | 2 | FE | Wire loseHeart() on wrong answers in lessons | P0 | 2 | Not Started
15 | 2 | FE | Coin balance display in navigation/top bar | P1 | 2 | Not Started
16 | 2 | FE | CosmeticShopView integration in Profile tab | P1 | 3 | Not Started
17 | 2 | FE | Heart refill sheet (spend 20 coins) | P1 | 2 | Not Started
18 | 2 | QA | Hearts edge cases: 0 hearts blocks lesson, regen across app restart | P0 | 3 | Not Started
19 | 2 | QA | Economy exploit testing: negative coins, double-spend | P0 | 2 | Not Started
20 | 2 | QA | Feeding animation and coin deduction accuracy | P1 | 2 | Not Started
21 | 3 | BE | Compendium unlock triggers tied to lesson completion | P0 | 3 | Not Started | 18 entries across 5 categories
22 | 3 | BE | Idle XP calculation: 2 XP/hr, max 48/24hr | P0 | 2 | Not Started
23 | 3 | BE | Pet abilities data: 24 abilities (3 per character × 8 characters) | P1 | 3 | Not Started | Unlock at tiers 2, 3, 4
24 | 3 | FE | CompendiumView integration in Skills tab | P0 | 3 | Not Started | Category filters, unlock states
25 | 3 | FE | Idle XP return overlay polish (WelcomeBackView animations) | P1 | 2 | Not Started
26 | 3 | FE | Pet abilities display on character profile | P1 | 3 | Not Started
27 | 3 | FE | Compendium entry detail view with code examples | P1 | 2 | Not Started
28 | 3 | QA | Compendium unlock accuracy (each lesson → correct entry) | P0 | 3 | Not Started
29 | 3 | QA | Idle XP timing precision across time zones | P1 | 2 | Not Started
30 | 3 | QA | Cross-system regression: hearts + pet care + economy together | P0 | 3 | Not Started
31 | 4 | BE | Firestore schema design for GameState fields | P0 | 3 | Not Started | users/{uid}/gameState
32 | 4 | BE | Cloud sync on every progress change (not just onboarding) | P0 | 4 | Not Started | Pending task from CLAUDE.md
33 | 4 | BE | Google Sign-In end-to-end testing & fixes | P0 | 4 | Not Started | Pending task from CLAUDE.md
34 | 4 | FE | UI polish pass: all 6 game system screens | P0 | 4 | Not Started | Consistent design language
35 | 4 | FE | Dark mode support for all new views | P1 | 3 | Not Started
36 | 4 | FE | Animation refinements (pet care, hearts, shop) | P1 | 3 | Not Started
37 | 4 | QA | Cloud sync conflict testing (two devices, offline/online) | P0 | 4 | Not Started
38 | 4 | QA | Full auth flow: email, Google, anonymous → onboarding → main | P0 | 3 | Not Started | Pending task from CLAUDE.md
39 | 4 | QA | Full new-user onboarding flow testing | P0 | 3 | Not Started | Pending task from CLAUDE.md
40 | 4 | Marketing | Draft App Store description and keywords | P1 | 3 | Not Started
41 | 5 | BE | Review and finalize all 16 lesson content | P0 | 4 | Not Started
42 | 5 | BE | Economy balance tuning (earn rates vs spend costs) | P0 | 3 | Not Started
43 | 5 | BE | Finalize 18 compendium entries (descriptions + code examples) | P1 | 3 | Not Started
44 | 5 | FE | Lesson content polish and visual consistency | P0 | 3 | Not Started
45 | 5 | FE | Cosmetic preview animations (try-on before buy) | P1 | 3 | Not Started
46 | 5 | FE | Sound effects for all game interactions | P1 | 2 | Not Started
47 | 5 | FE | Kingdom pixel art: upgrade Mystic Grove to 320×200 | P2 | 2 | Not Started | Currently 240×150
48 | 5 | QA | Full playthrough: new user → all 4 tiers complete | P0 | 6 | Not Started
49 | 5 | QA | Economy balance feedback report | P1 | 3 | Not Started
50 | 5 | Marketing | Create App Store screenshots (6 screens) | P1 | 4 | Not Started
51 | 5 | Marketing | Beta tester recruitment plan | P1 | 2 | Not Started
52 | 6 | BE | Build versioning and release notes | P0 | 2 | Not Started
53 | 6 | BE | Crash reporting setup (Firebase Crashlytics) | P0 | 3 | Not Started
54 | 6 | BE | Provisioning profiles and signing for TestFlight | P0 | 2 | Not Started
55 | 6 | FE | Final bug fixes from QA regression | P0 | 4 | Not Started
56 | 6 | FE | Performance optimization (scroll, animations, memory) | P1 | 3 | Not Started
57 | 6 | FE | App icon and launch screen finalization | P1 | 2 | Not Started
58 | 6 | QA | Full regression suite (all systems, all flows) | P0 | 6 | Not Started
59 | 6 | QA | Device testing (multiple macOS versions) | P0 | 3 | Not Started | macOS 13+
60 | 6 | QA | Beta tester onboarding walkthrough | P1 | 2 | Not Started
61 | 6 | Marketing | App Store listing finalized (description, keywords, screenshots) | P0 | 3 | Not Started
62 | 6 | Marketing | TestFlight invite emails and social announcement | P1 | 2 | Not Started
63 | 6 | Marketing | Privacy policy and support URL published | P0 | 2 | Not Started

## Timeline
Week | Dates | Sprint | FE | BE | QA | Marketing | Milestone
1 | Apr 14–18 | S1 | PetCareView integration | GameSystems merge | Build verification
2 | Apr 21–27 | S1 | WelcomeBackView overlay | GamePersistence wiring | Pet mood testing |  | Sprint 1 Review
3 | Apr 28–May 2 | S2 | HeartsView in lessons | Hearts regen timer
4 | May 5–11 | S2 | CosmeticShopView, coin UI | Coin economy logic | Hearts + economy QA |  | Sprint 2 Review
5 | May 12–16 | S3 | CompendiumView | Compendium unlocks
6 | May 19–25 | S3 | Idle XP overlay, abilities UI | Idle XP calc, abilities data | Cross-system regression |  | Sprint 3 Review
7 | May 26–30 | S4 | UI polish pass | Firestore schema | Auth flow testing
8 | Jun 1–8 | S4 | Dark mode, animations | Cloud sync, Google Sign-In | Cloud sync + onboarding QA | App Store draft | Sprint 4 Review
9 | Jun 9–13 | S5 | Lesson polish, cosmetic anims | Lesson review, balance | Full playthrough | Screenshots
10 | Jun 16–22 | S5 | Sound effects, Mystic Grove art | Compendium entries | Balance feedback | Beta recruitment | Sprint 5 Review
11 | Jun 23–27 | S6 | Final bug fixes | Build prep, Crashlytics | Full regression | Listing finalized
12 | Jun 30–Jul 5 | S6 | Performance opt | Signing + upload | Device testing | TestFlight invites | TESTFLIGHT LAUNCH

## Metrics
Sprint Metrics & KPIs
Metric | Target | Current | Status
Total Tasks | 63 | 0 | Not Started
P0 Tasks Completed | 32 | 0 | Not Started
Game Systems Integrated | 6 of 6 | 0 of 6 | Not Started
Lessons Reviewed | 16 of 16 | 0 of 16 | Not Started
Compendium Entries | 18 of 18 | 0 of 18 | Not Started
Cosmetic Items | 18 of 18 | 0 of 18 | Not Started
Cloud Sync Working | Yes | No | Not Started
Google Sign-In Working | Yes | No | Not Started
TestFlight Build Uploaded | Yes | No | Not Started
App Store Listing Ready | Yes | No | Not Started
Beta Testers Invited | 10+ | 0 | Not Started
Critical Bugs | 0 | - | Not Started